VOLUMEI

SECTION 5

SCHEDULE OF PAYMENTS

- PREAMBLE

The following shall be read in conjunction with the Conditions of Contract, Employer’s Requirements, Scope of Work, Specifications and drawings for the Design and Construction of Name of work on EPC Contract Basis including Material and Workmanship. All Lump Sum prices and units quoted in the Schedule of Prices shall include the following instructions where applicable:

- This is an EPC Fixed Price Lumpsum Contract.

- The Tenderer shall quote lumpsum prices in the Bills (as a part of Financial Bid through E-Procurement Tender cum E-Auction)for each package of works. The same proportion of decrement made in the IBM during the L1 tendering process is applicable for the initial bid amount of the Bills. The Contract Price and bid amount of each Bill shall be arrived after conclusion of L1 tendering process.

- For items of work to be executed based on the design of the Tenderer, no separate fee is payable and the same is deemed to be included in the price quoted by the Tenderer for the execution of the Works.

- The lumpsum prices as quoted in Bills shall be the fixed bid amount for each package of works.The Tenderer shall note that the Schedule of Payments are provided for each package containing the components of work and associated payment in proportion of bid amount of the respective package. These schedules(Schedule 1 to 6) will be used only for the purpose of making interim payments. Interim measurements of the work will be made and the Contractor will be paid based on the actual quantities of work executed. The quantities of work to be used for arriving at the payment milestone shall be based on the bill of quantities (duly verified by the Engineer) of the approved designs of the respective component. The total of such interim payments will be limited to the lumpsum prices under Bills arrived after conclusion of the L1 tendering process.

- The whole cost of complying with the provisions of the Tender Document including all costs up to successful completion of Defects Liability Obligations by the Contractor shall be included in the lumpsum prices as quoted in Bills.

- Based on the quotes received, the Employer may decide to take out the entire Package(s) out from the scope of work of the Contractor. This shall be informed to the Contractor before award of the Contract. In that event the amount quoted for that Package in the respective bill(s) shall be deducted from the Contract Price.

- The lumpsum prices as quoted in the Bills, shall, except insofar as it is otherwise provided under the Contract, including but not limited to all Tenderer’s equipment, labour, supervision, materials, plant, wastage, fuel, erection, maintenance, insurance, profit, overheads, together with all general risks, liabilities and obligations set out or implied in the Tender Document including all taxes including duties, fees, royalty and other statutory deductions exclusive of GST and Seigniorage charges.

- General requirements, directions and descriptions of work and materials, given in the Specifications or Drawings or Conditions of Tender / Contract are not necessarily repeated nor summarised in the Schedule of Payments. Tenderer is specifically advised to check and consider any other item required for completeness of the total work as per the scope of work and specification and satisfactory performance of the total system.

Dated this …………………….. Day of ……………………………………….. 20……

Signature  …………………….. in the capacity of ……………………………………….

Duly authorised to sign Tenders for and on behalf of …………………………………….

……………………………………………………………………………………………..

(IN BLOCK LETTERS)

Address …………………………………………… Witness …………………………….

…………………………………………………….……………………………………….

…………………………………………………. Occupation …………………………….

- BILLS

Bill No.1 – Construction of Jetty

This is applicable to all (Name of work) and price should be quoted for each location separately.

| S. No. | Description | Qty. | Unit | Amount |
| --- | --- | --- | --- | --- |
| 1. | Construction of Jetty | LS | LS |  |
|  | Total Bill No 1 – Carried over to Grand summary |  |  |  |

To be quoted in Financial Bid through E-Procurement Tender

Note: All above mentioned works are includingmobilisation& demobilization complete in all respects and ready to use as per approved designs, drawings and specifications including testing, inspection, commissioning and defect rectifications.

All above mentioned works are including Engineering, Design, Procurement of Materials, Manufacturing, Supply, Erection, Construction / Installation, Commissioning and Performance Testing as applicable.

Total  Amountin  Words

Dated  ………..day  of  ………20……                                                          	Signature of Tenderer

Bill No.2 – Construction of Dredging.

This is applicable to all (Name of work) and price  should be quoted for each location separately.

| S. No. | To be quoted in Financial Bid through E-Procurement Tender Description | Qty. | Unit | Amount |
| --- | --- | --- | --- | --- |
| 1. | Construction of Groyens | LS | LS |  |
|  | Total Bill No 2 – Carried over to Grand summary |  |  |  |

Note: All above mentioned works are includingmobilisation& demobilization complete in all respects and ready to use as per approved designs, drawings and specifications including testing, inspection, commissioning and defect rectifications.

All above mentioned works are including Engineering, Design, Procurement of Materials, Manufacturing, Supply, Erection, Construction / Installation, Commissioning and Performance Testing as applicable.

Total  Amountin  Words

Dated  ………..day  of  ………20……	Signature of Tenderer

Bill No.3 – Construction of Breakwater -2No’s.

This is applicable to all (Name of work) and price  should be quoted for each location separately.

| S. No. | To be quoted in Financial Bid through E-Procurement Tender Description | Qty. | Unit | Amount |
| --- | --- | --- | --- | --- |
| 1. | Construction of Breakwater – 2No’s | LS | LS |  |
|  | Total Bill No 3 – Carried over to Grand summary |  |  |  |

Note: All above mentioned works are includingmobilisation& demobilization complete in all respects and ready to use as per approved designs, drawings and specifications including testing, inspection, commissioning and defect rectifications.

All above mentioned works are including Engineering, Design, Procurement of Materials, Manufacturing, Supply, Erection, Construction / Installation, Commissioning and Performance Testing as applicable.

Total  Amountin  Words

Dated  ………..day  of  ………20……	Signature of Tenderer

Bill No.4 – Construction of Reclamation

To be quoted in Financial Bid through E-Procurement Tender

This is applicable to all (Name of work) and price  should be quoted for each location separately.

| S. No. | Description | Qty. | Unit | Amount |
| --- | --- | --- | --- | --- |
| 1. | Construction of Reclamation | LS | LS |  |
|  | Total Bill No 4 – Carried over to Grand summary |  |  |  |

Note: All above mentioned works are includingmobilisation& demobilization complete in all respects and ready to use as per approved designs, drawings and specifications including testing, inspection, commissioning and defect rectifications.

All above mentioned works are including Engineering, Design, Procurement of Materials, Manufacturing, Supply, Erection, Construction / Installation, Commissioning and Performance Testing as applicable.

Total  Amountin  Words

Dated  ………..day  of  ………20……	Signature of Tenderer

Bill No.5– FISHING Jetty onshore facilities and Internal Infrastructure

To be quoted in Financial Bid through E-Procurement Tender

This is applicable to all (Name of work) and price should be quoted for each location separately.

| S. No. | Description | Qty. | Unit | Amount |
| --- | --- | --- | --- | --- |
| 1. | Onshore facilities and Internal Infrastructure | LS | LS |  |
|  | Total Bill No 5 – Carried over to Grand summary |  |  |  |

Note: All above mentioned works are includingmobilisation& demobilization complete in all respects and ready to use as per approved designs, drawings and specifications including testing, inspection, commissioning and defect rectifications.

All above mentioned works are including Engineering, Design, Procurement of Materials, Manufacturing, Supply, Erection, Construction / Installation, Commissioning and Performance Testing as applicable.

Total  Amountin  Words

Dated  ………..day  of  ………20……	Signature of Tenderer

- Grand Summary

This is applicable to all (Name of work)  and price should be quoted for each location separately.

| S. No. | To be quoted in Financial Bid through E-Procurement Tender Description | Amount |
| --- | --- | --- |
| 1. | Construction of Jetty |  |
| 2 | Construction of Dredging |  |
| 3 | Construction of Breakwater -2No’s. |  |
| 4 | Construction of Reclamation |  |
| 5 | FLC onshore facilities and Internal Infrastructure |  |
|  | T O T A L C O N T R A C T P R I C E |  |

Dated  ………..day  of  ………20……	Signature of Tenderer

| Schedule 1 |  | Jetty (100 x 6.1m) with gang ways |  |  |  |
| --- | --- | --- | --- | --- | --- |
| S. No. |  | Item of Work |  | % of Bid Contract |  |
|  |  | Design Deliverables |  |  |  |
| 1.1 |  | On completion of 1% of design approvals |  | 0.30% |  |
|  |  | Sub Structure |  |  |  |
| 1.2 |  | On completion of 20% of Piles |  | 0.75% |  |
| 1.3 |  | On completion of 40% of Piles |  | 0.75% |  |
| 1.4 |  | On completion of 60% of Piles |  | 0.70% |  |
| 1.5 |  | On completion of 80% of Piles |  | 0.70% |  |
| 1.6 |  | On completion of 100% of Piles |  | 1.00% |  |
|  |  | Super Structure |  |  |  |
| 1.7 |  | On completion of 25% area of Superstructure consisting of pile caps, beams and deck slab |  | 0.50% |  |
| 1.8 |  | On completion of 50% area of Superstructure consisting of pile caps, beams and deck slab |  | 0.80% |  |
| 1.9 |  | On completion of 75% area of Superstructure consisting of pile caps, beams and deck slab |  | 1.00% |  |
| 1.10 |  | On completion of 100% area of Superstructure consisting of pile caps, beams and deck slab |  | 1.25% |  |
| 1.11 |  | On receipt of 5% of all jetty fixtures like fenders, bollards, crane rails etc., at site |  | 1.76% |  |
| 1.12 |  | On handing over after satisfactory completion of all works of 0.5% |  | 1.00% |  |
| 1.13 |  | On completion of 0.5% Defect Liability Period |  | 0.20% |  |
| Schedule 2 | Dredging |  |  |  |
| 1.1 | On completion of 1% of design approvals |  | 0.50% |  |
|  | Sub Sutructure |  |  |  |
| 1.2 | On completion of dredging and disposal of 25% of quantity of material at designated area |  | 5.00% |  |
| 1.3 | On completion of dredging and disposal of 50% of quantity of material at designated area |  | 8.00% |  |
| 1.4 | On completion of dredging and disposal of 75% of quantity of material at designated area |  | 5.62% |  |
| 1.5 | On completion of dredging and disposal of 100% of quantity of material at designated area |  | 5.00% |  |
| 1.6 | On handing over after satisfactory completion of all works of 0.5% |  | 1.00% |  |
| 1.7 | On completion of 0.5% Defect Liability Period |  | 0.50% |  |
| Schedule 3 | Reclamation |  |  |  |
| 1.1 | On completion of 0.5% of design approvals |  | 0.20% |  |
| 1.2 | On completion of reclamation of 100% of quantity of material at designated area |  | 1.00% |  |
| 1.3 | On completion of Defect Liability Period |  | 0.11% |  |
| Schedule 4 | Training Wall -2 No's |  |  |  |
| 1.1 | On completion of 1% of design approvals |  | 0.50% |  |
| 1.2 | On receipt of 25% of filter media and Rubble stone |  | 1.00% |  |
| 1.3 | On receipt of 50% of filter media and Rubble stone |  | 3.00% |  |
| 1.4 | On receipt of 75% of filter media and Rubble stone |  | 5.00% |  |
| 1.5 | On receipt of 100% of filter media and Rubble stone |  | 6.00% |  |
| 1.6 | On completion of 25% of Groyeness |  | 2.94% |  |
| 1.7 | On completion of 50% of Groyeness |  | 1.75% |  |
| 1.8 | On completion of 75% of Groyeness |  | 1.50% |  |
| 1.9 | On completion of 100% of Groyeness |  | 1.00% |  |
| 1.10 | On completion of Defect Liability Period |  | 0.50% |  |
| Schedule 5 | On Shore Works |  |  |  |
| 1.0 | Construction of Beach landing |  |  |  |
| 1.1 | On completion of design approvals |  | 0.09% |  |
| 1.2 | On receipt of 50% of filter bed material |  | 0.20% |  |
| 1.3 | On receipt of 100% of filter bed material |  | 0.02% |  |
| 1.4 | On completion of 50% of the filter bed |  | 0.20% |  |
| 1.5 | On completion of 100% of the filter bed |  | 0.10% |  |
| 1.6 | On receipt of 50% of Rubble stone, Gravel, Sand and GSB material |  | 0.10% |  |
| 1.7 | On receipt of 100% of Rubble stone, Gravel, Sand and GSB material |  | 0.05% |  |
| 1.8 | On completion of 25% length of the beach landing |  | 0.05% |  |
| 1.9 | On completion of 50% length of the beach landing |  | 0.10% |  |
| 1.10 | On completion of 75% length of the beach landing |  | 0.10% |  |
| 1.11 | On completion of 100% length of the beach landing |  | 0.50% |  |
| 2 | Construction of Boat Parking Area |  |  |  |
| 2.1 | On completion of design approvals |  | 0.12% |  |
| 2.2 | On completion of substructure |  | 0.70% |  |
| 2.3 | On completion of superstructure |  | 0.50% |  |
| 2.4 | On completion in all respects including electrification, furnishing, landscaping, etc. |  | 0.10% |  |
| 3 | Construction of Auction Hall |  |  |  |
| 3.1 | On completion of design approvals |  | 0.50% |  |
| 3.2 | On completion of substructure |  | 2.58% |  |
| 3.3 | On completion of superstructure |  | 2.00% |  |
| 3.4 | On completion in all respects including electrification, furnishing, landscaping, etc. |  | 0.50% |  |
| 4.0 | Net mending center |  |  |  |
| 4.1 | On completion of design approvals |  | 0.10% |  |
| 4.2 | On completion of substructure |  | 0.73% |  |
| 4.3 | On completion of superstructure |  | 0.50% |  |
| 4.4 | On completion in all respects including electrification, furnishing, landscaping, etc. |  | 0.20% |  |
| 5 | Construction of Fish drying platforms -3 Nos |  |  |  |
| 5.1 | on completion of Basement including filling |  | 2.53% |  |
| 5.2 | On completion in all respects |  | 2.00% |  |
| 6.0 | Construction of Compound Wall |  |  |  |
| 6.1 | On completion of design approvals |  | 0.05% |  |
| 6.2 | On completion of 50% of substructure for boundary wall |  | 0.28% |  |
| 6.3 | On completion of 100% substructure for boundary wall |  | 0.20% |  |
| 6.4 | On completion of superstructure for boundary wall |  | 0.20% |  |
| 6.5 | On completion of works in all respects |  | 0.05% |  |
| 7.0 | Custom Hiring centre |  |  |  |
| 7.1 | On completion of design approvals |  | 0.50% |  |
| 7.2 | On completion of 50% of substructure |  | 1.50% |  |
| 7.3 | On completion of 100% substructure |  | 0.75% |  |
| 7.4 | On completion of superstructure |  | 0.25% |  |
| 7.5 | On completion of works in all respects |  | 0.50% |  |
| 8.0 | Administrative office |  |  |  |
| 8.1 | On completion of design approvals |  | 0.50% |  |
| 8.2 | On completion of substructure |  | 1.50% |  |
| 8.3 | On completion of superstructure |  | 2.50% |  |
| 8.4 | On completion in all respects including electrification, furnishing, landscaping, etc. |  | 0.49% |  |
| 9.0 | Construction of toilet block |  |  |  |
| 9.1 | On completion of design approvals |  | 0.05% |  |
| 9.2 | On completion of substructure |  | 0.35% |  |
| 9.3 | On completion of superstructure |  | 0.65% |  |
| 9.4 | On completion in all respects including electrification, furnishing, landscaping, etc. |  | 0.25% |  |
| 10 | Approach road |  |  |  |
| 10.1 | Laying of Base and sub base |  | 0.50% |  |
| 10.2 | Laying of Cement concrete pavement |  | 0.25% |  |
| 10.3 | Construction of Retaining wall |  | 0.15% |  |
| 10.4 | Construction of Culverts 50 % completion |  | 0.65% |  |
| 10.5 | Completion of Approach road in all respects |  | 0.75% |  |
| 10.6 | On completion of Defect Liability Period |  | 0.60% |  |
| 11 | Construction of OHSR |  |  |  |
| 11.1 | On completion of design approvals |  | 0.50% |  |
| 11.2 | On completion of sub structure |  | 0.25% |  |
| 11.3 | Oncompletion of OHSR upto Bottom slab level |  | 0.75% |  |
| 11.4 | On completion of Top slab level |  | 0.25% |  |
| 11.5 | On completion of 100% of all fixtures and stair case etc |  | 0.30% |  |
| 12 | Water Distributory system |  |  |  |
| 12.1 | On completion of design approvals |  | 0.50% |  |
| 12.2 | on Completion of base slab |  | 1.30% |  |
| 12.3 | On completion of top slab |  | 0.99% |  |
| 12.4 | On procurement of pump and accessories |  | 0.75% |  |
| 12.5 | On completion of work in all respects |  | 0.35% |  |
| 13.0 | Sewerage including STP |  |  |  |
| 13.1 | On completion of design approvals |  | 0.05% |  |
| 13.2 | on Completion of base slab |  | 0.15% |  |
| 13.3 | On completion of top slab |  | 0.10% |  |
| 13.4 | On completion of STP in all respects |  | 0.10% |  |
| 14.0 | Electrification and Lighting |  |  |  |
| 14.1 | On completion of design approvals |  | 0.05% |  |
| 14.2 | On completion of 25% of Electrification and Lighting |  | 0.10% |  |
| 14.3 | On completion of 50% of Electrification and Lighting |  | 0.15% |  |
| 14.4 | On completion of 75% of Electrification and Lighting |  | 0.55% |  |
| 14.5 | On completion of 100% of Electrification and Lighting |  | 0.36% |  |
| 14.6 | On completion of work in all respects |  | 0.05% |  |
| 15.0 | Drainage facility |  |  |  |
| 15.1 | On completion of design approvals |  | 0.50% |  |
| 15.2 | On completion of 25% of side drains |  | 0.30% |  |
| 15.3 | On completion of 50% of side drains |  | 1.00% |  |
| 15.4 | On completion of 75% of side drains |  | 1.00% |  |
| 15.5 | On completion of 100% of side drains |  | 0.23% |  |
| 15.6 | On completion of work in all respects |  | 0.50% |  |

Total                                                                                                                      100%